## App
Title/Screen Name | Feature Names | Sub feature | QA (Unity Team) (Name) | Priority | Functional | Animation | Sound | Pixel Perfect | Bug report
Splash Screen |  |  | Not QA | MVP Feature | Full Functional | N/A | Missing | Yes |  | Ekanta
Loading Screen | Loading Progress with Voices |  | Not QA | MVP Feature | Partial Working | N/A | Missing | Yes | Even after the loading screen is 100% complete, the logging screen does not open immediately
On Boarding | Galary |  | Not QA | After MVP | Not Ready | N/A | N/A | No
| Language |  | Not QA | After MVP | Partial Working | N/A | N/A | Yes | Language can not change
| Login |  | Not QA | MVP Feature | Full Functional | N/A | Missing | Yes
| Account Open |  | Not QA | MVP Feature | Full Functional | N/A | Missing | No
| Skip |  | Not QA | MVP Feature | Full Functional | N/A | Done | Yes
Sign up page | Mobile / Email | Formate Checking | Not QA | MVP Feature | Partial Working | N/A | N/A | Yes | Only sign in with mail can't use phone number
Password screen | Password | Formate | Not QA | MVP Feature | Full Functional | N/A | N/A | Yes
Varification page | OTP-Box |  | Not QA | MVP Feature | Partial Working | N/A | N/A | N/A | Even if I provide wrong otp, email is getting verified
| Not found OTP |  | Not QA | MVP Feature | Not Ready
| OTP Email Formate |  | Not QA | After MVP | Partial Working | N/A | N/A | No
| OTP SMS Formate |  | Not QA | After MVP | Not Ready | N/A | N/A | Yes
Varification Successfull page | Shown successfull message |  | Not QA | MVP Feature | Full Functional | N/A | N/A | Yes
| Check In Terms |  | Not QA | MVP Feature | Not Ready | N/A | N/A | N/A | No trems and condition checkbox
| Treams & Condition |  | Not QA | MVP Feature | Not Ready |  |  |  |  | Tinni
Parents information page | Parents Name |  | Not QA | MVP Feature | Full Functional | N/A | N/A | Yes
| Password |  | Not QA | MVP Feature | Full Functional | N/A | N/A | Yes
| Confirm Password |  | Not QA | MVP Feature | Not Ready | N/A
kids page | Child nickname |  | Not QA | MVP Feature | Full Functional | N/A
Kids info page | Select gender |  | Not QA | MVP Feature | Full Functional | N/A | N/A | Yes
| Select age |  | Not QA | MVP Feature | Full Functional | N/A |  | Yes
Kids profile | Camara Picture add |  | Not QA | MVP Feature | Full Functional |  |  | Yes
| OR- Select avatar |  | Not QA | MVP Feature | Full Functional |  |  | Yes
Guest Mode | Guest profile |  | Not QA | MVP Feature | Not Ready
| Leson (Completed) |  | Not QA | MVP Feature | Not Ready
| Leson (In-Progress) |  | Not QA | MVP Feature | Not Ready
| Leson (Lock) |  | Not QA | MVP Feature | Not Ready
| Score Board (Lock) |  | Not QA | MVP Feature | Not Ready
| Tom Game |  | Not QA | MVP Feature | Not Ready | N/A | Missing | Yes
| AR - Scaner |  | Not QA | MVP Feature | Not Ready
| AR - Scaner (Alternative) |  | Not QA | MVP Feature | Not Ready
| All in one |  | Not QA | MVP Feature | Not Ready
| Book pdf download |  | Not QA | MVP Feature | Not Ready | N/A | N/A
| Part 3 and next all lock |  | Not QA | MVP Feature | Not Ready | N/A | Have Issue | No
| Play Button |  | Not QA | MVP Feature | Full Functional
| Parents control |  | Not QA | MVP Feature | Not Ready | N/A | Missing | No
| Music |  | Not QA | MVP Feature | Not Ready
User -(Inactive page ) | Fetures list Guest Mode |  | Not QA | MVP Feature | Not Ready
Activation Page | Activate the book |  | Not QA | MVP Feature | Full Functional | N/A | N/A | No | The feature is showing. But could not check the feature due to lack of QR code | Maher
| No Book |  | Not QA | MVP Feature | Not Ready | N/A | N/A | No | Book Orede page can't shown
| Not now |  | Not QA | MVP Feature | Full Functional | N/A | N/A | Yes
Congratulation window | Shown successfull message (With voice ) |  | Not QA | MVP Feature | Not Ready |  | Missing | No
Book Order page | Oreder Button |  | Not QA | MVP Feature | Not Ready | N/A | N/A | N/A | Orede page can't shown
| Free Download pdf |  | Not QA | MVP Feature | Not Ready | N/A | N/A | No
Child Profiel Section | Kids name |  | Not QA | After MVP | Full Functional |  |  | No
| Score bar |  | Not QA | After MVP | Not Ready
leaderboard | leader board |  | Not QA | After MVP | Not Ready
AR Camara Feature shot | Detection of Book image (AR Scan) |  |  | MVP Feature
| rotate-360 |  | Not QA | MVP Feature | Not Ready |  | N/A | N/A
| play-circle |  | Not QA | MVP Feature | Not Ready |  | N/A | N/A
| Sound |  | Not QA | MVP Feature | Not Ready
| Scannig Progress Bar |  | Not QA | MVP Feature | Not Ready
| Complete Button |  | Not QA | MVP Feature | Not Ready
AR Camara Alternative (Non Supported AR device) | Detection AR Device status |  |  | MVP Feature
| Notice intro page |  |  | MVP Feature
| 3D images Galary |  |  | MVP Feature
| 3D images Galary (lock and unlock) |  |  | MVP Feature
| rotate-360 |  |  | MVP Feature
| play-circle |  |  | MVP Feature
| Sound |  |  | MVP Feature
| Scannig Progress Bar |  |  | MVP Feature
| Complete Button |  |  | MVP Feature
AR Camara Feature shot | All unlock images |  |  | MVP Feature
Librery section (All In One) | Bangla |  | Not QA | MVP Feature | Partial Working |  | Have Issue | No
| English |  | Not QA | MVP Feature | Partial Working |  | Have Issue | No
| Math |  | Not QA | MVP Feature | Partial Working |  | Have Issue | No | Sound is not working in full Arabic numbers
| Arabic |  | Not QA | MVP Feature | Full Functional |  | Done | No
| Chora (bangla) |  | Not QA | MVP Feature | Partial Working |  | Done | No | play বাটনের জায়গায় push বাটন ব্যবহার করা হয়েছে
| Rhymse |  | Not QA | MVP Feature | Partial Working |  | Done | No
| Flowers |  | Not QA | MVP Feature | Partial Working |  | Have Issue | No
| Fruits |  | Not QA | MVP Feature | Partial Working |  | Missing | No
| Animal |  | Not QA | MVP Feature | Partial Working |  | Done | No
| National |  | Not QA | MVP Feature | Partial Working |  | Done | No
| Sessason |  | Not QA | MVP Feature | Full Functional |  | Done | No
| 12 months (English) |  | Not QA | MVP Feature | Full Functional |  | Done | No
| Bangla 12 months |  | Not QA | MVP Feature | Full Functional |  | Done | No
| 7 DAYS (NGLISH) |  | Not QA | MVP Feature | Partial Working |  | Have Issue | No
| 7 DAYS (Bangla) |  | Not QA | MVP Feature | Full Functional |  | Have Issue | No
| My body part |  | Not QA | MVP Feature | Partial Working |  | Have Issue | No | "Ears" sound missing
| Directions |  | Not QA | MVP Feature | Full Functional |  | Have Issue | No | English Sound Missing
| Colors |  | Not QA | MVP Feature | Partial Working |  | Have Issue | No | White, Orange, Violet, Colors Sound Missing
| Back Button |  |  | MVP Feature | Not Ready |  | N/A | N/A
Parental control | Home |  | Not QA |  | Not Ready |  |  |  | Parental control button not working.
| Parents profile |  | Not QA |  | Partial Working |  |  | No
| Child Profile |  | Not QA |  | Partial Working |  |  | No
| Setting |  | Not QA |  | Full Functional |  |  | No
| About us |  | Not QA |  | Not Ready
| Feed back |  | Not QA |  | Partial Working |  |  | No
Parental control - Home | Message From CEO |  |  | MVP Feature
| Follow us |  |  | After MVP
| Parants Comment |  |  | After MVP
| Rate |  |  | After MVP
| Feedback |  |  | After MVP
| More App |  |  | After MVP
Parental control - Profile | Parents Section |  |  | After MVP
| Edit and Change password |  |  | After MVP
| View Child Details |  |  | After MVP
| Add Child |  |  | After MVP
Parental control - Setting | Selct Lang |  |  | After MVP
| Backgroudn Music |  |  | MVP Feature | Not Ready
| Sound |  |  | After MVP | Not Ready
| Logout |  |  | MVP Feature | Full Functional
Parental control - About US | About |  |  | MVP Feature
| Developed by |  |  | MVP Feature
| Follow us |  |  | MVP Feature
| More App |  |  | After MVP
Parental control - Feedback | Parants Comments |  |  | After MVP
| Share your feedback |  |  | After MVP
Tom game Module | Game Logic |  | Not QA | After MVP | Not Ready
| Game Playgin |  | Not QA | After MVP | Not Ready
| Tom mood(sleppy) |  |  | After MVP
| Tom mood (Hungry) |  |  | After MVP
| Game Reminder |  |  | After MVP
Rating | Rating |  | Not QA | After MVP | Not Ready |  |  |  | Parental control button not working.
| Rating Active |  | Not QA | After MVP | Not Ready
Lesson 1 | Introduction |  | Not QA | MVP Feature | Not Ready | N/A | Missing | N/A | Back button not working
| About Bangaldesh |  | Not QA | MVP Feature | Not Ready |  | Have Issue
| Play with Tom |  | Not QA | MVP Feature | Not Ready | N/A | Done
Common Lesson Features | Learn (Step 1) |  | Not QA | MVP Feature | Full Functional | N/A | Done | Yes
| Congratulation page (after 5 taps) |  |  | MVP Feature | Partial Working | N/A | Done | Yes | Congratulations window does not appear immediately after TAP 5 times
| match up (Step 2) |  | Not QA | MVP Feature | Full Functional | N/A | Done | Yes
| Learn with pictures (Step 3) |  | Not QA | MVP Feature | Full Functional | N/A | Done | Yes
| Read the book AR (Step 4) |  | Not QA | MVP Feature | Not Ready
Learn (Step 1) | Intro Page |  |  | MVP Feature | Partial Working | N/A | Missing | Yes
| Kids user real pic |  |  | MVP Feature | Not Ready | N/A | N/A | N/A
| Voice play |  |  | MVP Feature | Not Ready | N/A | Missing | Yes
| Waiting until voice play (repet button) |  |  | MVP Feature | Full Functional | N/A | Done
| 5 Times Repeat |  |  | MVP Feature | Full Functional |  | Done
| 1 increment score & food icon with one play |  |  | MVP Feature | Full Functional
| Congratulations after 5 repeat |  |  | MVP Feature | Partial Working |  |  |  | Congratulations window does not appear immediately after TAP 5 times
match up (Step 2) | Intro Page |  |  | MVP Feature | Not Ready
| Kids user real pic |  |  | MVP Feature | Not Ready
| Voice play (ask question) |  |  | MVP Feature | Not Ready
| Repeat (ask question) |  |  | MVP Feature | Not Ready
| Right sound |  |  | MVP Feature | Not Ready
| Wrong sound |  |  | MVP Feature | Not Ready
| 1 increment score & food icon (if right) |  |  | MVP Feature | Not Ready
| ensure all Quize (e.g ABCD or 12345) |  |  | MVP Feature | Not Ready
| Congratulations after done |  |  | MVP Feature | Not Ready
Learn with pictures (Step 3) | Intro Page |  |  | MVP Feature | Not Ready
| Voice play (ask question) |  |  | MVP Feature | Not Ready
| Kids user real pic |  |  | MVP Feature | Not Ready
| Voice play (e.g a for apple) |  |  | MVP Feature | Full Functional |  | Done | Yes
| Waiting until voice play (repet button) |  |  | MVP Feature | Not Ready
| 5 Times Repeat |  |  | MVP Feature | Full Functional |  | Missing | Yes
| 1 increment score & food icon with one play |  |  | MVP Feature
| Congratulations after 5 repeat |  |  | MVP Feature | Not Ready |  |  |  | Congratulations window does not appear immediately after TAP 5 times
Read the book AR (Step 4) | Intro Page |  |  | MVP Feature | Not Ready
| Voice play (ask question) |  |  | MVP Feature | Not Ready
| Kids user real pic |  |  | MVP Feature | Not Ready
| Instruction to open book |  |  | MVP Feature | Not Ready
| AR Camara Feature |  |  | MVP Feature | Not Ready
| Detection AR availablity |  |  | MVP Feature | Not Ready
| AR alternative |  |  | MVP Feature | Not Ready
Lesson 2 |  |  |  | MVP Feature
Lesson 3 |  |  |  | MVP Feature | Not Ready
Lesson 4 |  |  |  | MVP Feature | Not Ready
Lesson 5 |  |  |  | MVP Feature | Not Ready
Lesson 6 |  |  |  | MVP Feature | Not Ready
Lesson 7 |  |  |  | MVP Feature | Not Ready
Lesson 8 |  |  |  | MVP Feature | Not Ready
Lesson 9 |  |  |  | MVP Feature | Not Ready
Lesson 10 |  |  |  | MVP Feature | Not Ready
Lesson 11 |  |  |  | MVP Feature | Not Ready
Lesson 12 |  |  |  | After MVP | Not Ready
Lesson 13 |  |  |  | After MVP | Not Ready
Lesson 14 |  |  |  | After MVP | Not Ready
Lesson 15 |  |  |  | After MVP | Not Ready
Lesson 16 |  |  |  | After MVP | Not Ready
Lesson 17 |  |  |  | After MVP | Not Ready
Lesson 18 |  |  |  | After MVP | Not Ready
Lesson 19 |  |  |  | After MVP | Not Ready
Lesson 20 |  |  |  | After MVP | Not Ready
Lesson 21 |  |  |  | After MVP | Not Ready
Lesson 22 |  |  |  | After MVP | Not Ready
Lesson 23 |  |  |  | After MVP | Not Ready
Lesson 24 |  |  |  | After MVP | Not Ready
Lesson 25 |  |  |  | After MVP | Not Ready
Lesson 26 |  |  |  | After MVP | Not Ready
Lesson 27 |  |  |  | After MVP | Not Ready
Lesson 28 |  |  |  | After MVP | Not Ready
Lesson 29 |  |  |  | After MVP | Not Ready
Lesson 30 |  |  |  | After MVP | Not Ready
Lesson 31 |  |  |  | After MVP | Not Ready
Lesson 32 |  |  |  | After MVP | Not Ready
Lesson 33 |  |  |  | After MVP | Not Ready

## App_11-12
Title/Screen Name | Feature Names | Sub feature | QA (Unity Team) (Name) | Priority | Functional | Animation | Sound | Pixel Perfect | Bug report
Splash Screen |  |  | Not QA | MVP Feature | Full Functional | N/A | Missing | Yes |  | Ekanta
Loading Screen | Loading Progress with Voices |  | Not QA | MVP Feature | Partial Working | N/A | Missing | Yes | Even after the loading screen is 100% complete, the logging screen does not open immediately
On Boarding | Galary |  | Not QA | After MVP | Not Ready | N/A | N/A | No
| Language |  | Not QA | After MVP | Partial Working | N/A | N/A | Yes | Language can not change
| Login |  | Not QA | MVP Feature | Full Functional | N/A | Missing | Yes
| Account Open |  | Not QA | MVP Feature | Full Functional | N/A | Missing | No
| Skip |  | Not QA | MVP Feature | Full Functional | N/A | Done | Yes
Sign up page | Mobile / Email | Formate Checking | Not QA | MVP Feature | Partial Working | N/A | N/A | Yes | Only sign in with mail can't use phone number
Password screen | Password | Formate | Not QA | MVP Feature | Full Functional | N/A | N/A | Yes
Varification page | OTP-Box |  | Not QA | MVP Feature | Partial Working | N/A | N/A | N/A | Even if I provide wrong otp, email is getting verified
| Not found OTP |  | Not QA | MVP Feature | Not Ready
| OTP Email Formate |  | Not QA | After MVP | Partial Working | N/A | N/A | No
| OTP SMS Formate |  | Not QA | After MVP | Not Ready | N/A | N/A | Yes
Varification Successfull page | Shown successfull message |  | Not QA | MVP Feature | Full Functional | N/A | N/A | Yes
| Check In Terms |  | Not QA | MVP Feature | Not Ready | N/A | N/A | N/A | No trems and condition checkbox
| Treams & Condition |  | Not QA | MVP Feature | Not Ready |  |  |  |  | Tinni
Parents information page | Parents Name |  | Not QA | MVP Feature | Full Functional | N/A | N/A | Yes
| Password |  | Not QA | MVP Feature | Full Functional | N/A | N/A | Yes
| Confirm Password |  | Not QA | MVP Feature | Not Ready | N/A
kids page | Child nickname |  | Not QA | MVP Feature | Full Functional | N/A
Kids info page | Select gender |  | Not QA | MVP Feature | Full Functional | N/A | N/A | Yes
| Select age |  | Not QA | MVP Feature | Full Functional | N/A |  | Yes
Kids profile | Camara Picture add |  | Not QA | MVP Feature | Full Functional |  |  | Yes
| OR- Select avatar |  | Not QA | MVP Feature | Full Functional |  |  | Yes
Guest Mode | Guest profile |  | Not QA | MVP Feature | Not Ready
| Leson (Completed) |  | Not QA | MVP Feature | Not Ready
| Leson (In-Progress) |  | Not QA | MVP Feature | Not Ready
| Leson (Lock) |  | Not QA | MVP Feature | Not Ready
| Score Board (Lock) |  | Not QA | MVP Feature | Not Ready
| Tom Game |  | Not QA | MVP Feature | Not Ready | N/A | Missing | Yes
| AR - Scaner |  | Not QA | MVP Feature | Not Ready
| AR - Scaner (Alternative) |  | Not QA | MVP Feature | Not Ready
| All in one |  | Not QA | MVP Feature | Not Ready
| Book pdf download |  | Not QA | MVP Feature | Not Ready | N/A | N/A
| Part 3 and next all lock |  | Not QA | MVP Feature | Not Ready | N/A | Have Issue | No
| Play Button |  | Not QA | MVP Feature | Full Functional
| Parents control |  | Not QA | MVP Feature | Not Ready | N/A | Missing | No
| Music |  | Not QA | MVP Feature | Not Ready
User -(Inactive page ) | Fetures list Guest Mode |  | Not QA | MVP Feature | Not Ready
Activation Page | Activate the book |  | Not QA | MVP Feature | Full Functional | N/A | N/A | No | The feature is showing. But could not check the feature due to lack of QR code | Maher
| No Book |  | Not QA | MVP Feature | Not Ready | N/A | N/A | No | Book Orede page can't shown
| Not now |  | Not QA | MVP Feature | Full Functional | N/A | N/A | Yes
Congratulation window | Shown successfull message (With voice ) |  | Not QA | MVP Feature | Not Ready |  | Missing | No
Book Order page | Oreder Button |  | Not QA | MVP Feature | Not Ready | N/A | N/A | N/A | Orede page can't shown
| Free Download pdf |  | Not QA | MVP Feature | Not Ready | N/A | N/A | No
Child Profiel Section | Kids name |  | Not QA | After MVP | Full Functional |  |  | No
| Score bar |  | Not QA | After MVP | Not Ready
leaderboard | leader board |  | Not QA | After MVP | Not Ready
AR Camara Feature shot | Detection of Book image (AR Scan) |  |  | MVP Feature
| rotate-360 |  | Not QA | MVP Feature | Not Ready |  | N/A | N/A
| play-circle |  | Not QA | MVP Feature | Not Ready |  | N/A | N/A
| Sound |  | Not QA | MVP Feature | Not Ready
| Scannig Progress Bar |  | Not QA | MVP Feature | Not Ready
| Complete Button |  | Not QA | MVP Feature | Not Ready
AR Camara Alternative (Non Supported AR device) | Detection AR Device status |  |  | MVP Feature
| Notice intro page |  |  | MVP Feature
| 3D images Galary |  |  | MVP Feature
| 3D images Galary (lock and unlock) |  |  | MVP Feature
| rotate-360 |  |  | MVP Feature
| play-circle |  |  | MVP Feature
| Sound |  |  | MVP Feature
| Scannig Progress Bar |  |  | MVP Feature
| Complete Button |  |  | MVP Feature
AR Camara Feature shot | All unlock images |  |  | MVP Feature
Librery section (All In One) | Bangla |  | Not QA | MVP Feature | Partial Working |  | Have Issue | No
| English |  | Not QA | MVP Feature | Partial Working |  | Have Issue | No
| Math |  | Not QA | MVP Feature | Partial Working |  | Have Issue | No | Sound is not working in full Arabic numbers
| Arabic |  | Not QA | MVP Feature | Full Functional |  | Done | No
| Chora (bangla) |  | Not QA | MVP Feature | Partial Working |  | Done | No | play বাটনের জায়গায় push বাটন ব্যবহার করা হয়েছে
| Rhymse |  | Not QA | MVP Feature | Partial Working |  | Done | No
| Flowers |  | Not QA | MVP Feature | Partial Working |  | Have Issue | No
| Fruits |  | Not QA | MVP Feature | Partial Working |  | Missing | No
| Animal |  | Not QA | MVP Feature | Partial Working |  | Done | No
| National |  | Not QA | MVP Feature | Partial Working |  | Done | No
| Sessason |  | Not QA | MVP Feature | Full Functional |  | Done | No
| 12 months (English) |  | Not QA | MVP Feature | Full Functional |  | Done | No
| Bangla 12 months |  | Not QA | MVP Feature | Full Functional |  | Done | No
| 7 DAYS (NGLISH) |  | Not QA | MVP Feature | Partial Working |  | Have Issue | No
| 7 DAYS (Bangla) |  | Not QA | MVP Feature | Full Functional |  | Have Issue | No
| My body part |  | Not QA | MVP Feature | Partial Working |  | Have Issue | No | "Ears" sound missing
| Directions |  | Not QA | MVP Feature | Full Functional |  | Have Issue | No | English Sound Missing
| Colors |  | Not QA | MVP Feature | Partial Working |  | Have Issue | No | White, Orange, Violet, Colors Sound Missing
| Back Button |  |  | MVP Feature | Not Ready |  | N/A | N/A
Parental control | Home |  | Not QA |  | Not Ready |  |  |  | Parental control button not working.
| Parents profile |  | Not QA |  | Partial Working |  |  | No
| Child Profile |  | Not QA |  | Partial Working |  |  | No
| Setting |  | Not QA |  | Full Functional |  |  | No
| About us |  | Not QA |  | Not Ready
| Feed back |  | Not QA |  | Partial Working |  |  | No
Parental control - Home | Message From CEO |  |  | MVP Feature
| Follow us |  |  | After MVP
| Parants Comment |  |  | After MVP
| Rate |  |  | After MVP
| Feedback |  |  | After MVP
| More App |  |  | After MVP
Parental control - Profile | Parents Section |  |  | After MVP
| Edit and Change password |  |  | After MVP
| View Child Details |  |  | After MVP
| Add Child |  |  | After MVP
Parental control - Setting | Selct Lang |  |  | After MVP
| Backgroudn Music |  |  | MVP Feature | Not Ready
| Sound |  |  | After MVP | Not Ready
| Logout |  |  | MVP Feature | Full Functional
Parental control - About US | About |  |  | MVP Feature
| Developed by |  |  | MVP Feature
| Follow us |  |  | MVP Feature
| More App |  |  | After MVP
Parental control - Feedback | Parants Comments |  |  | After MVP
| Share your feedback |  |  | After MVP
Tom game Module | Game Logic |  | Not QA | After MVP | Not Ready
| Game Playgin |  | Not QA | After MVP | Not Ready
| Tom mood(sleppy) |  |  | After MVP
| Tom mood (Hungry) |  |  | After MVP
| Game Reminder |  |  | After MVP
Rating | Rating |  | Not QA | After MVP | Not Ready |  |  |  | Parental control button not working.
| Rating Active |  | Not QA | After MVP | Not Ready
Lesson 1 | Introduction |  | Not QA | MVP Feature | Not Ready | N/A | Missing | N/A | Back button not working
| About Bangaldesh |  | Not QA | MVP Feature | Not Ready |  | Have Issue
| Play with Tom |  | Not QA | MVP Feature | Not Ready | N/A | Done
Common Lesson Features | Learn (Step 1) |  | Not QA | MVP Feature | Full Functional | N/A | Done | Yes
| Congratulation page (after 5 taps) |  |  | MVP Feature | Partial Working | N/A | Done | Yes | Congratulations window does not appear immediately after TAP 5 times
| match up (Step 2) |  | Not QA | MVP Feature | Full Functional | N/A | Done | Yes
| Learn with pictures (Step 3) |  | Not QA | MVP Feature | Full Functional | N/A | Done | Yes
| Read the book AR (Step 4) |  | Not QA | MVP Feature | Not Ready
Learn (Step 1) | Intro Page |  |  | MVP Feature | Partial Working | N/A | Missing | Yes
| Kids user real pic |  |  | MVP Feature | Not Ready | N/A | N/A | N/A
| Voice play |  |  | MVP Feature | Not Ready | N/A | Missing | Yes
| Waiting until voice play (repet button) |  |  | MVP Feature | Full Functional | N/A | Done
| 5 Times Repeat |  |  | MVP Feature | Full Functional |  | Done
| 1 increment score & food icon with one play |  |  | MVP Feature | Full Functional
| Congratulations after 5 repeat |  |  | MVP Feature | Partial Working |  |  |  | Congratulations window does not appear immediately after TAP 5 times
match up (Step 2) | Intro Page |  |  | MVP Feature | Not Ready
| Kids user real pic |  |  | MVP Feature | Not Ready
| Voice play (ask question) |  |  | MVP Feature | Not Ready
| Repeat (ask question) |  |  | MVP Feature | Not Ready
| Right sound |  |  | MVP Feature | Not Ready
| Wrong sound |  |  | MVP Feature | Not Ready
| 1 increment score & food icon (if right) |  |  | MVP Feature | Not Ready
| ensure all Quize (e.g ABCD or 12345) |  |  | MVP Feature | Not Ready
| Congratulations after done |  |  | MVP Feature | Not Ready
Learn with pictures (Step 3) | Intro Page |  |  | MVP Feature | Not Ready
| Voice play (ask question) |  |  | MVP Feature | Not Ready
| Kids user real pic |  |  | MVP Feature | Not Ready
| Voice play (e.g a for apple) |  |  | MVP Feature | Full Functional |  | Done | Yes
| Waiting until voice play (repet button) |  |  | MVP Feature | Not Ready
| 5 Times Repeat |  |  | MVP Feature | Full Functional |  | Missing | Yes
| 1 increment score & food icon with one play |  |  | MVP Feature
| Congratulations after 5 repeat |  |  | MVP Feature | Not Ready |  |  |  | Congratulations window does not appear immediately after TAP 5 times
Read the book AR (Step 4) | Intro Page |  |  | MVP Feature | Not Ready
| Voice play (ask question) |  |  | MVP Feature | Not Ready
| Kids user real pic |  |  | MVP Feature | Not Ready
| Instruction to open book |  |  | MVP Feature | Not Ready
| AR Camara Feature |  |  | MVP Feature | Not Ready
| Detection AR availablity |  |  | MVP Feature | Not Ready
| AR alternative |  |  | MVP Feature | Not Ready
Lesson 2 |  |  |  | MVP Feature
Lesson 3 |  |  |  | MVP Feature | Not Ready
Lesson 4 |  |  |  | MVP Feature | Not Ready
Lesson 5 |  |  |  | MVP Feature | Not Ready
Lesson 6 |  |  |  | MVP Feature | Not Ready
Lesson 7 |  |  |  | MVP Feature | Not Ready
Lesson 8 |  |  |  | MVP Feature | Not Ready
Lesson 9 |  |  |  | MVP Feature | Not Ready
Lesson 10 |  |  |  | MVP Feature | Not Ready
Lesson 11 |  |  |  | MVP Feature | Not Ready
Lesson 12 |  |  |  | After MVP | Not Ready
Lesson 13 |  |  |  | After MVP | Not Ready
Lesson 14 |  |  |  | After MVP | Not Ready
Lesson 15 |  |  |  | After MVP | Not Ready
Lesson 16 |  |  |  | After MVP | Not Ready
Lesson 17 |  |  |  | After MVP | Not Ready
Lesson 18 |  |  |  | After MVP | Not Ready
Lesson 19 |  |  |  | After MVP | Not Ready
Lesson 20 |  |  |  | After MVP | Not Ready
Lesson 21 |  |  |  | After MVP | Not Ready
Lesson 22 |  |  |  | After MVP | Not Ready
Lesson 23 |  |  |  | After MVP | Not Ready
Lesson 24 |  |  |  | After MVP | Not Ready
Lesson 25 |  |  |  | After MVP | Not Ready
Lesson 26 |  |  |  | After MVP | Not Ready
Lesson 27 |  |  |  | After MVP | Not Ready
Lesson 28 |  |  |  | After MVP | Not Ready
Lesson 29 |  |  |  | After MVP | Not Ready
Lesson 30 |  |  |  | After MVP | Not Ready
Lesson 31 |  |  |  | After MVP | Not Ready
Lesson 32 |  |  |  | After MVP | Not Ready
Lesson 33 |  |  |  | After MVP | Not Ready

## App Status Map
Title/Screen Name | Feature Names
Guest |  |  | Registerd | Premium
Splash Screen
Loading Screen | Loading Progress with Voices
On Boarding | Galary
Language
| Account Open |  | Login
Sign up page | Mobile
| Email | wrong adress (incoming), Wrong formating
Password screen | Password | matach not works
Varification page | OTP-Box | wrong OTP works
| Not found OTP | not working
OTP Email Formate
OTP SMS Formate
Varification Successfull page | Shown successfull message
Check In Terms
Terms & Condition link
Parents information page | Parents Name
Password
Confirm Password
kids page | Child nickname
Kids info page | Select gender
Select age
Kids profile | Camara Picture add | not user frindly, scaled, not working with avatar
OR- Select avatar
Guest Mode | Guest profile
Leson (Completed)
Leson (In-Progress)
Leson (Lock)
Score Board (Lock)
| Tom Game | few issues, no sound
| AR - Scaner | not checked
AR - Scaner (Alternative)
All in one
Book pdf download
Part 3 and next all lock
Play Button
Parents control
Music
User -(Inactive page ) | Fetures list Guest Mode
Activation Page | Activate the book
No Book
Not now
Congratulation window | Shown successfull message (With voice )
Book Order page | Oreder Button
Free Download pdf
Child Profiel Section | Kids name
Score bar
leaderboard | leader board
AR Camara Feature shot | Detection of Book image (AR Scan)
rotate-360
play-circle
Sound
Scannig Progress Bar
Complete Button
AR Camara Alternative (Non Supported AR device) | Detection AR Device status
Notice intro page
3D images Galary
3D images Galary (lock and unlock)
rotate-360
play-circle
Sound
Scannig Progress Bar
Complete Button
AR Camara Feature shot | All unlock images
Librery section (All In One) | Bangla
English
Math
Arabic
Chora (bangla)
Rhymse
Flowers
Fruits
Animal
National
Sessason
12 months (English)
Bangla 12 months
7 DAYS (NGLISH)
7 DAYS (Bangla)
My body part
Directions
Colors
Back Button
Parental control | Home
Parents profile
Child Profile
Setting
About us
Feed back
Parental control - Home | Message From CEO
Follow us
Parants Comment
Rate
Feedback
More App
Parental control - Profile | Parents Section
Edit and Change password
View Child Details
Add Child
Parental control - Setting | Selct Lang
Backgroudn Music
Sound
Logout
Parental control - About US | About
Developed by
Follow us
More App
Parental control - Feedback | Parants Comments
Share your feedback
Tom game Module | Game Logic
Game Playgin
Tom mood(sleppy)
Tom mood (Hungry)
Game Reminder
Rating | Rating
Rating Active
Lesson 1 | Introduction
About Bangaldesh
Play with Tom
Common Lesson Features | Learn (Step 1)
Congratulation page (after 5 taps)
match up (Step 2)
Learn with pictures (Step 3)
Read the book AR (Step 4)
Learn (Step 1) | Intro Page
Kids user real pic
Voice play
Waiting until voice play (repet button)
5 Times Repeat
1 increment score & food icon with one play
Congratulations after 5 repeat
match up (Step 2) | Intro Page
Kids user real pic
Voice play (ask question)
Repeat (ask question)
Right sound
Wrong sound
1 increment score & food icon (if right)
ensure all Quize (e.g ABCD or 12345)
Congratulations after done
Learn with pictures (Step 3) | Intro Page
Voice play (ask question)
Kids user real pic
Voice play (e.g a for apple)
Waiting until voice play (repet button)
5 Times Repeat
1 increment score & food icon with one play
Congratulations after 5 repeat
Read the book AR (Step 4) | Intro Page
Voice play (ask question)
Kids user real pic
Instruction to open book
AR Camara Feature
Detection AR availablity
AR alternative
Lesson 2
Lesson 3
Lesson 4
Lesson 5
Lesson 6
Lesson 7
Lesson 8
Lesson 9
Lesson 10
Lesson 11
Lesson 12
Lesson 13
Lesson 14
Lesson 15
Lesson 16
Lesson 17
Lesson 18
Lesson 19
Lesson 20
Lesson 21
Lesson 22
Lesson 23
Lesson 24
Lesson 25
Lesson 26
Lesson 27
Lesson 28
Lesson 29
Lesson 30
Lesson 31
Lesson 32
Lesson 33

## Web
Title/Screen Name | Feature Names | QA (Unity Team) (Name) | Functional | Animation | Sound | Pixel Perfect | Bug report
Nav bar | Home | Not QA | Not Ready
| About | Not QA | Not Ready
| Blog | Not QA | Not Ready
| Contacts | Not QA | Not Ready
| Cart | Not QA | Not Ready
| Searc bar | Not QA | Not Ready
| My account | Not QA | Not Ready
Hero Sectopns | Play store link | Not QA | Not Ready
| App store link | Not QA | Not Ready
| Buy book bitton | Not QA | Not Ready
About Section
Main feature sections
Apps Activity Section
FAQ Section
Footer Section | Social Link
Home
Parents profile
Child Profile
Setting
About us
Feed back
Tom mood(sleppy)
Tom mood (Hungry)
Rating
Rating Active

## Copy of App
Title/Screen Name | Feature Names | Sub feature | QA (Unity Team) (Name) | Priority | Functional | Animation | Sound | Pixel Perfect | Bug report
Splash Screen |  |  | Not QA | MVP Feature | Full Functional | Not Working |  | No |  | Ekanta
Loading Screen | Loading Progress with Voices |  | Not QA | MVP Feature | Partial Working | Working | N/A | No
On Boarding | Galary |  | Not QA | After MVP | Not Ready | N/A | N/A | No
| Language |  | Not QA | After MVP | Partial Working | Not Working | N/A | Yes | Language can not change
| Login |  | Not QA | MVP Feature | Not Ready | Not Working | N/A | No
| Account Open |  | Not QA | MVP Feature | Partial Working | Not Working | N/A | No
| Skip |  | Not QA | MVP Feature | Full Functional | Working | N/A | Yes
Sign up page | Mobile / Email | Formate Checking | Not QA | MVP Feature | Partial Working | N/A | N/A | No | Only sign in with mail can't use phone number
Password screen | Password | Formate | Not QA | MVP Feature | Full Functional | Not Working | N/A | No
Varification page | OTP-Box |  | Not QA | MVP Feature | Full Functional | Working | N/A | Yes
| Not found OTP |  | Not QA | MVP Feature | Not Ready
| OTP Email Formate |  | Not QA | After MVP | Partial Working | N/A | N/A | No
| OTP SMS Formate |  | Not QA | After MVP | Not Ready | N/A | N/A | Yes
Varification Successfull page | Shown successfull message |  | Not QA | MVP Feature | Full Functional | Working | N/A | Yes
| Check In Terms |  | Not QA | MVP Feature | Not Ready | N/A | N/A | N/A | No trems and condition checkbox
| Treams & Condition |  | Not QA | MVP Feature | Not Ready |  |  |  |  | Tinni
Parents information page | Parents Name |  | Not QA | MVP Feature | Not Ready
| Password |  | Not QA | MVP Feature | Partial Working |  |  | No
| Confirm Password |  | Not QA | MVP Feature | Not Ready | N/A
kids page | Child nickname |  | Not QA | MVP Feature | Full Functional | Working
Kids info page | Select gender |  | Not QA | MVP Feature | Partial Working | Have Issue |  | No
| Select age |  | Not QA | MVP Feature | Partial Working | Have Issue |  | No
Kids profile | Camara Picture add |  | Not QA | MVP Feature | Not Ready
| OR- Select avatar |  | Not QA | MVP Feature | Not Ready
Guest Mode | Guest profile |  | Not QA | MVP Feature | Not Ready
| Leson (Completed) |  | Not QA | MVP Feature | Not Ready
| Leson (In-Progress) |  | Not QA | MVP Feature | Not Ready
| Leson (Lock) |  | Not QA | MVP Feature | Not Ready
| Score Board (Lock) |  | Not QA | MVP Feature | Not Ready
| Tom Game |  | Not QA | MVP Feature | Not Ready | Not Working | Missing | Yes
| AR - Scaner |  | Not QA | MVP Feature | Not Ready
| AR - Scaner (Alternative) |  | Not QA | MVP Feature | Not Ready
| All in one |  | Not QA | MVP Feature | Not Ready
| Book pdf download |  | Not QA | MVP Feature | Not Ready | N/A | N/A
| Part 3 and next all lock |  | Not QA | MVP Feature | Not Ready | N/A | Have Issue | No
| Play Button |  | Not QA | MVP Feature | Not Ready
| Parents control |  | Not QA | MVP Feature | Not Ready | N/A | Missing | No
| Music |  | Not QA | MVP Feature | Not Ready
User -(Inactive page ) | Fetures list Guest Mode |  | Not QA | MVP Feature | Not Ready
Activation Page | Activate the book |  | Not QA | MVP Feature | Partial Working | N/A | N/A | No | The feature is showing. But could not check the feature due to lack of QR code | Maher
| No Book |  | Not QA | MVP Feature | Partial Working | N/A | N/A | No | Orede page can't shown
| Not now |  | Not QA | MVP Feature | Full Functional | N/A | N/A | Yes
Congratulation window | Shown successfull message (With voice ) |  | Not QA | MVP Feature | Partial Working |  | Missing | No
Book Order page | Oreder Button |  | Not QA | MVP Feature | Partial Working | N/A | N/A | N/A | Orede page can't shown
| Free Download pdf |  | Not QA | MVP Feature | Partial Working | N/A | N/A | No
Child Profiel Section | Kids name |  | Not QA | After MVP | Not Ready
| Score bar |  | Not QA | After MVP | Not Ready
leaderboard | leader board |  | Not QA | After MVP | Not Ready
AR Camara Feature shot | Detection of Book image (AR Scan) |  |  | MVP Feature
| rotate-360 |  | Not QA | MVP Feature | Not Ready |  | N/A | N/A
| play-circle |  | Not QA | MVP Feature | Not Ready |  | N/A | N/A
| Sound |  | Not QA | MVP Feature | Not Ready
| Scannig Progress Bar |  | Not QA | MVP Feature | Not Ready
| Complete Button |  | Not QA | MVP Feature | Not Ready
AR Camara Alternative (Non Supported AR device) | Detection AR Device status |  |  | MVP Feature
| Notice intro page |  |  | MVP Feature
| 3D images Galary |  |  | MVP Feature
| 3D images Galary (lock and unlock) |  |  | MVP Feature
| rotate-360 |  |  | MVP Feature
| play-circle |  |  | MVP Feature
| Sound |  |  | MVP Feature
| Scannig Progress Bar |  |  | MVP Feature
| Complete Button |  |  | MVP Feature
AR Camara Feature shot | All unlock images |  |  | MVP Feature
Librery section (All In One) | Bangla |  | Not QA | MVP Feature | Partial Working |  | Have Issue | No
| English |  | Not QA | MVP Feature | Partial Working |  | Have Issue | No
| Math |  | Not QA | MVP Feature | Partial Working |  | Have Issue | No | Sound is not working in full Arabic numbers
| Arabic |  | Not QA | MVP Feature | Full Functional |  | Done | No
| Chora (bangla) |  | Not QA | MVP Feature | Partial Working |  | Done | No | play বাটনের জায়গায় push বাটন ব্যবহার করা হয়েছে
| Rhymse |  | Not QA | MVP Feature | Partial Working |  | Done | No
| Flowers |  | Not QA | MVP Feature | Partial Working |  | Have Issue | No
| Fruits |  | Not QA | MVP Feature | Partial Working |  | Missing | No
| Animal |  | Not QA | MVP Feature | Partial Working |  | Done | No
| National |  | Not QA | MVP Feature | Partial Working |  | Done | No
| Sessason |  | Not QA | MVP Feature | Full Functional |  | Done | No
| 12 months (English) |  | Not QA | MVP Feature | Full Functional |  | Done | No
| Bangla 12 months |  | Not QA | MVP Feature | Full Functional |  | Done | No
| 7 DAYS (NGLISH) |  | Not QA | MVP Feature | Full Functional |  | Missing | No
| 7 DAYS (Bangla) |  | Not QA | MVP Feature | Full Functional |  | Done | No
| My body part |  | Not QA | MVP Feature | Partial Working |  | Have Issue | No | "Ears" sound missing
| Directions |  | Not QA | MVP Feature | Full Functional |  | Have Issue | No | English Sound Missing
| Colors |  | Not QA | MVP Feature | Partial Working |  | Have Issue | No | White, Orange, Violet, Colors Sound Missing
| Back Button |  |  | MVP Feature | Not Ready |  | N/A | N/A
Parental control | Home |  | Not QA |  | Not Ready |  |  |  | Parental control button not working.
| Parents profile |  | Not QA |  | Not Ready
| Child Profile |  | Not QA |  | Not Ready
| Setting |  | Not QA |  | Not Ready
| About us |  | Not QA |  | Not Ready
| Feed back |  | Not QA |  | Not Ready
Parental control - Home | Message From CEO |  |  | MVP Feature
| Follow us |  |  | After MVP
| Parants Comment |  |  | After MVP
| Rate |  |  | After MVP
| Feedback |  |  | After MVP
| More App |  |  | After MVP
Parental control - Profile | Parents Section |  |  | After MVP
| Edit and Change password |  |  | After MVP
| View Child Details |  |  | After MVP
| Add Child |  |  | After MVP
Parental control - Setting | Selct Lang |  |  | After MVP
| Backgroudn Music |  |  | MVP Feature
| Sound |  |  | After MVP
| Logout |  |  | MVP Feature
Parental control - About US | About |  |  | MVP Feature
| Developed by |  |  | MVP Feature
| Follow us |  |  | MVP Feature
| More App |  |  | After MVP
Parental control - Feedback | Parants Comments |  |  | After MVP
| Share your feedback |  |  | After MVP
Tom game Module | Game Logic |  | Not QA | After MVP | Not Ready
| Game Playgin |  | Not QA | After MVP | Not Ready
| Tom mood(sleppy) |  |  | After MVP
| Tom mood (Hungry) |  |  | After MVP
| Game Reminder |  |  | After MVP
Rating | Rating |  | Not QA | After MVP | Not Ready |  |  |  | Parental control button not working.
| Rating Active |  | Not QA | After MVP | Not Ready
Lesson 1 | Introduction |  | Not QA | MVP Feature | Not Ready | Have Issue | Missing | N/A | Back button not working
| About Bangaldesh |  | Not QA | MVP Feature | Not Ready
| Play with Tom |  | Not QA | MVP Feature | Not Ready
Common Lesson Features | Learn (Step 1) |  | Not QA | MVP Feature | Not Ready |  |  |  | The feature is showing. But could not check the feature due to lack of QR code
| match up (Step 2) |  | Not QA | MVP Feature | Not Ready
| Learn with pictures (Step 3) |  | Not QA | MVP Feature | Not Ready
| Read the book AR (Step 4) |  | Not QA | MVP Feature | Not Ready
Learn (Step 1) | Intro Page |  |  | MVP Feature
| Kids user real pic |  |  | MVP Feature
| Voice play |  |  | MVP Feature
| Waiting until voice play (repet button) |  |  | MVP Feature
| 5 Times Repeat |  |  | MVP Feature
| 1 increment score & food icon with one play |  |  | MVP Feature
| Congratulations after 5 repeat |  |  | MVP Feature
match up (Step 2) | Intro Page |  |  | MVP Feature
| Kids user real pic |  |  | MVP Feature
| Voice play (ask question) |  |  | MVP Feature
| Repeat (ask question) |  |  | MVP Feature
| Right sound |  |  | MVP Feature
| Wrong sound |  |  | MVP Feature
| 1 increment score & food icon (if right) |  |  | MVP Feature
| ensure all Quize (e.g ABCD or 12345) |  |  | MVP Feature
| Congratulations after done |  |  | MVP Feature
Learn with pictures (Step 3) | Intro Page |  |  | MVP Feature
| Voice play (ask question) |  |  | MVP Feature
| Kids user real pic |  |  | MVP Feature
| Voice play (e.g a for apple) |  |  | MVP Feature
| Waiting until voice play (repet button) |  |  | MVP Feature
| 5 Times Repeat |  |  | MVP Feature
| 1 increment score & food icon with one play |  |  | MVP Feature
| Congratulations after 5 repeat |  |  | MVP Feature
Read the book AR (Step 4) | Intro Page |  |  | MVP Feature
| Voice play (ask question) |  |  | MVP Feature
| Kids user real pic |  |  | MVP Feature
| Instruction to open book |  |  | MVP Feature
| AR Camara Feature |  |  | MVP Feature
| Detection AR availablity |  |  | MVP Feature
| AR alternative |  |  | MVP Feature
Lesson 2 |  |  |  | MVP Feature
Lesson 3 |  |  |  | MVP Feature | Not Ready
Lesson 4 |  |  |  | MVP Feature | Not Ready
Lesson 5 |  |  |  | MVP Feature | Not Ready
Lesson 6 |  |  |  | MVP Feature | Not Ready
Lesson 7 |  |  |  | MVP Feature | Not Ready
Lesson 8 |  |  |  | MVP Feature | Not Ready
Lesson 9 |  |  |  | MVP Feature | Not Ready
Lesson 10 |  |  |  | MVP Feature | Not Ready
Lesson 11 |  |  |  | MVP Feature | Not Ready
Lesson 12 |  |  |  | After MVP | Not Ready
Lesson 13 |  |  |  | After MVP | Not Ready
Lesson 14 |  |  |  | After MVP | Not Ready
Lesson 15 |  |  |  | After MVP | Not Ready
Lesson 16 |  |  |  | After MVP | Not Ready
Lesson 17 |  |  |  | After MVP | Not Ready
Lesson 18 |  |  |  | After MVP | Not Ready
Lesson 19 |  |  |  | After MVP | Not Ready
Lesson 20 |  |  |  | After MVP | Not Ready
Lesson 21 |  |  |  | After MVP | Not Ready
Lesson 22 |  |  |  | After MVP | Not Ready
Lesson 23 |  |  |  | After MVP | Not Ready
Lesson 24 |  |  |  | After MVP | Not Ready
Lesson 25 |  |  |  | After MVP | Not Ready
Lesson 26 |  |  |  | After MVP | Not Ready
Lesson 27 |  |  |  | After MVP | Not Ready
Lesson 28 |  |  |  | After MVP | Not Ready
Lesson 29 |  |  |  | After MVP | Not Ready
Lesson 30 |  |  |  | After MVP | Not Ready
Lesson 31 |  |  |  | After MVP | Not Ready
Lesson 32 |  |  |  | After MVP | Not Ready
Lesson 33 |  |  |  | After MVP | Not Ready

## Dashboard
Title/Screen Name | Feature Names | QA (Unity Team) (Name) | Functional | Animation | Sound | Pixel Perfect | Bug report
Login | Email Import field | Inprogress | Full Functional | N/A |  | Yes
Password Import field
Sign In Button
Forgot Password
Remember me Check box
Navbar | Search
Notification
Profile
Admin Role
Dashboard Home | Total Users:- Premium, Register, Guest
New Users:- Premium, Register, Guest
Kids Profile:- Total, Boys, Girls
New Kids Profile:- Total, Boys, Girls
User Pie Chart
Voice Status:- Total Pending, Boys, Girls, Filter
Leaderboard:- Kids name, Points, See More
New Kids Profile list Table
New Kids Profile list Table :- Filter
New Kids Profile list Table :- View ( Action)
New Kids Profile list Table :- Edit ( Action)
New Kids Profile list Table :- Delete ( Action)
Search | Name
User ID
User Type
Date
App User Account | Parent Account
Parent Account:- All
Parent Account:- Premium
Parent Account:- Register
Parent Account:- Guest
Parent Account Search
Parent Account Filter
Parent Account View (Action )
Parent Account Edit (Action )
Parent Account Delete (Action )
Kids Profile
Kids Profile Search
Kids ProfileFilter
Kids Profile Progress Bar
Kids Profile View (Action )
Kids Profile Edit (Action )
Kids Profile Delete (Action )
Guest User
Guest User Search
Guest User Filter
Guest User View (Action )
Guest User Edit (Action )
Guest User Delete (Action )
Admin User | Create New User Button
Admin User Search
Admin User Filter
View (action)
Edit (action)
Delete (Action)
Create New User Page
Create New User Page back Button
Create New User Page Submit Button
Edit Admin Users Page
Edit Admin User back Button
Edit Admin Users save Button
Generate QR | Select Product Check Box
Generate New QR
Generate New QR Bulk
Generate
QR Code Print
QR Code Download (PDF)
New QR Bulk Generate
Back Button
Print QR ( QR Management ) | Generate QR Cord Button
Unpainted QR Code
Search
Product Dopdown
Print Now Button
New Check Box
Unprinted Check Box
Custom Check Box
Printed QR (QR Management) | Generate QR Cord Button
Unstickered QR Code
Product Dopdown
Search
New Check Box
New Check Box
Custom Check Box
Stickered Button
Action buttons (Edit, View, Delete)
Stickered (QR Management) | Product Dopdown
Search
New Check Box
New Check Box
Custom Check Box
Expired Button
Action buttons (Edit, View, Delete)
Generate QR Cord Button
Expired (QR Management) | Search Button
Product Dopdown Button
Action buttons (Edit, View, Delete)
Generate QR Cord Button
Push Notification | Title Text Field
Message Text Field
Send Button
Cancel Button
Back Button
Voice Upload | Total Pending (Voice Status)
Boys (Voice Status)
Girls (Voice Status)
Search
Filter Dopdown
All Check box
New Check box
Not uploaded Check box
Uploaded Check box
View (Action Button)
Edit (Action Button)
Upload (Action Button)
Voice Upload Page | Back Button
File Upload Field
Cancel Button
Continue Button
Feedback | Back Button
Search
Filter Dopdown
View (Action Button)
Edit (Action Button)
Checked status
Uncheched status
Issue status
Feedback View Pop Up | Close Button
Massage
Checked Button
Issue Button
Product | Add Product
Products List
Product Details
Search
Filter
View (Action Button)
Edit (Action Button)
Delete (Action Button)
Product Details Pop Up | Close Button
Product Details
Add Product | Back Button
Product name Import field
Select Product type
import product logo
import product cover image
Submit Button

## AR Status
Title/ Alphabet | QA (Unity Team) (Name) | AR Detection Quality | Functional | Animation | Sound | Pixel Perfect | Bug report
অ
আ
ই
ঈ
উ
ঊ
ঋ
এ
ঐ
ও
ঔ
ক
খ
গ
ঘ
ঙ
চ
ছ
জ
ঝ
ঞ
ট
ঠ
ড
ঢ
ণ
ত
থ
দ
ধ
ন
প
ফ
ব
ভ
ম
য
র
ল
শ
ষ
স
হ
ক্ষ
ড়
ঢ়
য়
ৎ
ং
ঃ
ঁ
A
B
C
D
E
F
G
H
I
J
K
L
M
N
O
P
Q
R
S
T
U
V
W
X
Y
Z